## project
Team 2
[8 empty] | Step | [6 empty] | Project
ACTIVITY | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
 | time axis 2015-03-13 to 2015-05-11
Design Phase - Mechanical
Movement design | bar: 2015-03-13 to 2015-04-03
Concept | bar: 2015-03-13 to 2015-03-19
Verification | bar: 2015-03-20 to 2015-03-22
Layout - Parts and specifications | bar: 2015-03-23 to 2015-03-27
Verification 2 & Ordering | bar: 2015-03-28 to 2015-04-03
Mount design | bar: 2015-03-13 to 2015-04-03
Concept | bar: 2015-03-13 to 2015-03-19
Verification | bar: 2015-03-20 to 2015-03-22
Layout - Size and Parts | bar: 2015-03-23 to 2015-03-27
Verification 2 & Ordering | bar: 2015-03-28 to 2015-04-03
Design Phase - Electrical
Arduino Power Circuit | bar: 2015-03-13 to 2015-04-03
Schematic design | bar: 2015-03-13 to 2015-03-19
Schematic verification & ordering | bar: 2015-03-20 to 2015-03-27
Build and test | bar: 2015-03-28 to 2015-04-03
Arduino Control Circuit | bar: 2015-03-13 to 2015-04-03
Schematic design | bar: 2015-03-13 to 2015-03-19
Schematic verification & ordering | bar: 2015-03-20 to 2015-03-27
Build and test | bar: 2015-03-28 to 2015-04-03
Arduino Control Code | bar: 2015-03-13 to 2015-03-27
Preliminary code | bar: 2015-03-13 to 2015-03-19
Debug and Verification | bar: 2015-03-20 to 2015-03-27
Build Phase | bar: 2015-04-04 to 2015-04-24
Mount and Movement compile | bar: 2015-04-04 to 2015-04-11
Schematic compile | bar: 2015-04-04 to 2015-04-11
Merge mech. And elec. Designs | bar: 2015-04-12 to 2015-04-24
Test Phase | bar: 2015-04-25 to 2015-05-08
Movement | bar: 2015-04-25
Control | bar: 2015-04-26
Power | bar: 2015-04-26
Extended Test | bar: 2015-04-27 to 2015-04-30
Final Checks | bar: 2015-05-01 to 2015-05-08
Need movement mechanism for control code